## Implementation Milestones
HOW TO USE THIS TEMPLATE: Use this template to set out your milestones at each stage of your implementation. Keep track of your milestone status, your anticipated and actual completion timeline, and the resources you'll need in order to achieve each task. You can then use this timeline to provide updates to shareholders on your progress. *NOTE: Examples provided are not based on a real implementation timeline. Do not rely on these as a standard timeline for your onboarding with Marketo Engage, as every implementation is unique with different milestones and requirements according to your organization's needs.
Topic | Milestone | Status | Anticipated Date | Actual Date | Resources Needed
Use these general onboarding topics to organize the stages of your milestones. | Write out your specific milestone tasks. | What is the current status of your task? | What is the aniticipated completion date of this task? | When was this task actually completed? | What resources will you need to complete this task and which team(s) will you need them from?
Technical Setup
| EXAMPLE: Install MunchkinID on the company website | Complete | 2024-09-05 | 2024-09-12 | Web Development team
| EXAMPLE: Set up Domain Keys Identified Mail (DKIM) and 2 separate CNAMEs for deliverability and email tracking links. | Complete | 2024-09-15 | 2024-09-18 | Support and setup from the IT Team.
Adobe Admin Console & Admin Setup
| EXAMPLE: Create Marketo Engage users and roles | Complete | 2024-08-27 | 2024-09-15 | Information from marketing teams on who needs access to Marketo Engage.
| EXAMPLE: Create additional Marketo Engage Product Admin in Adobe Admin Console | Complete | 2024-08-27 | 2024-09-15 | Information from marketing operation team on who needs admin access to Marketo Engage.
| EXAMPLE: Set up Support Administrators | Complete | 2024-08-27 | 2024-09-15 | Information from marketing operation team to confirm the main contacts for support. Support from System Admin to assign Support Admin users.
| EXAMPLE: Define folder structure and naming conventions | Complete | 2024-09-07 | 2024-09-12 | Input from each team using Marketo Engage on program types and organization needs.
CRM Integration(if apply)
| EXAMPLE: Determine field mapping prior to sync | In Progress | 2024-10-22 | N/A | Support from CRM admin to understand available fields.
| EXAMPLE: Conduct a data audit | In Progress | 2024-10-26 | N/A | Support from CRM admin or budget.
Operational Program Build
| EXAMPLE: Create program to standardize incoming data | Not Started | 2024-11-09 | N/A | Support from the Sales Ops and CRM teams to determine a data management strategy.
| EXAMPLE: Create an email subscription center | Not Started | 2024-11-19 | N/A | Input from the marketing teams on content types and segmentation for mailing lists.
First Marketing Program Build
| EXAMPLE: Set up basic email program | In Progress | 2024-11-12 | N/A | Creative assets from digital team for emails and landing pages.
| EXAMPLE: Create program for quarterly newsletter | Not Started | 2024-11-30 | N/A | Content from marketing team for newsletter email and creative assets/content from the design team.
LaunchPoint Integration Setup
| EXAMPLE: Create API only user and role | Not Started | 2024-11-23 | N/A | Scope out the services needed for the new instance with the marketing teams.
| EXAMPLE: Create a custom service for Google Ads. | Not Started | 2024-12-07 | N/A | Support from Web and Paid Media teams to authenticate Marketo Engage to access Google Ads.
User Training and Documentation
| EXAMPLE: Create a governance guide for internal users | Not Started | 2024-12-02 | N/A | Create a Marketo Engage governance team to build supporting governance documentation or budget to contract the governance project out.
| EXAMPLE: Train 4 users and provide them with Standard Marketo User access | Not Started | 2024-12-13 | N/A | Support from VP of Marketing to make trainings mandatory for access to Marketo Engage.
Go-Live
| EXAMPLE: Send first newsletter | Not Started | 2024-12-09 | N/A | Marketing Operations team to QA, schedule, and send.
| EXAMPLE: Pull the first Email Performance Report | Not Started | 2024-12-16 | N/A | Marketing Operations team to QA, schedule, and send.